## Blank
Sprint Backlog for Project:
Story ID | Resource | Story/Task | Time Required | Time Remaining
User Story
Task 1
Task 2
Task 3
Task 4
Task 5
User Story
Task 1
Task 2
Task 3
Task 4
Task 5
User Story
Task 1
Task 2
Task 3
Task 4
Task 5
User Story
Task 1
Task 2
Task 3
Task 4
Task 5

## Example
Sprint Backlog for Project: Coffee Shop App
Story ID | Resource | Story/Task | Time Required (Hours) | Time Remaining (Hours)
0001 Customer Needs 1 | Lead: Ram | User Story: Easy Access to Orders | 77
| Marvin | Task 1: Develop visible drop-down menu | 20
| Marvin | Task 2: List easy to view pricing for all menu options | 15
| Don | Task 3: Develop secure payment transaction feature | 30
| Mona | Task 4: Develop order confirmation acknowledgement function | 12
Task 5
0002 Employee Needs 1 | Lead: Sally | User Story: Real-Time Access to Orders | 30
| Kyoko | Task 1: Develop visual order confirmation screen | 10
| Priya | Task 2: Program capability to see customer's name | 5
| Priya | Task 3: Clearly display order pick-up time | 5
| Harold | Task 4: List any applicable special instructions | 5
| Harold | Task 5: Automatically generate label when order is complete | 5
User Story
Task 1
Task 2
Task 3
Task 4
Task 5
User Story
Task 1
Task 2
Task 3
Task 4
Task 5
Total Sprint Hours |  |  | 107 | 0